## NAS ToBe
Set Name | UUID | SDU/MDU | Order type | Type | Unit count | Status code | HV-S | UV-S | HV-NE4 | UV-NE4 | GIS Planung | Fremdleitungsplan | Genehmigungen | Tiefbau | Spleißen | Einblasen | Gartenbohrung | Hauseinführung | HÜP | Leitungsweg NE4 | GFTA | ONT | Patch | GIS Dokumentaion**
Desktop | [6 empty] | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
App | [6 empty] | ● | ● | ● | ● |  |  |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | ●
BoQ | [6 empty] | HBG-1 | HBG-1 |  |  | PLA-1 | TBA-1 | TBA-1 | TBA-1 | SPL-1 | EIN-1 | TBA-1 | MON-6 | MON-5 |  | MON-4 | MON-2 | MON-3
GC Routing | [6 empty] | untrennbar |  |  |  |  | untrennbar + Gartenbohrung |  |  |  |  | untrennbar
SDU-GFTAL-HTP | Unit | SDU | GFTAL | NE3 (HTP) | NA | 100
SDU-GFTAL-HTP | Unit | SDU | GFTAL | NE3 (HTP) | NA | 101
SDU-GFTAL-HTP | Unit | SDU | GFTAL | NE3 (HTP) | NA | 102
SDU-GFTAL-HTP | Unit | SDU | GFTAL | NE3 (HTP) | NA | 103
SDU-GFTAL-HTP | Unit | SDU | GFTAL | NE3 (HTP) | NA | 108
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 100
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 101
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 102
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 103
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 108
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 100
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 101
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 102
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 103
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 108
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 100
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 101
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 102
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 103
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 108
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 100
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 101 |  |  |  | Multiple | [10 empty] | Multiple
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 102 |  |  |  | Multiple | [10 empty] | Multiple
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 103 |  |  |  | Multiple | [10 empty] | Multiple
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 108 |  |  |  | Multiple | [10 empty] | Multiple
SDU-GFTAL-NE3 (HTP) | Unit | SDU | GFTAL | NE3 (HTP) | NA | 107
SDU-GFTAL-NE3 (HTP) | Unit | SDU | GFTAL | NE3 (HTP) | NA | 109
SDU-GFTAL-NE3 (HTP) | Unit | SDU | GFTAL | NE3 (HTP) | NA | 105
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 107
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 109
SDU-GFTAL-NE4 | Unit | SDU | GFTAL | NE4 | 1 | 105
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 107
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 109
MDU-GFTAL-NE4 | Unit | MDU | GFTAL | NE4 | >1 | 105
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 107
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 109
MDU-PHA Standard-NA | Building | MDU | PHA Standard | NA | NA | 105
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 107 |  |  |  | Multiple | [10 empty] | Multiple
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 109 |  |  |  | Multiple | [10 empty] | Multiple
MDU-PHA Full Expansion-NE4 | Building | MDU | PHA Full Expansion | NE4 | >=3 | 105 |  |  |  | Multiple | [10 empty] | Multiple
Tasks for GIS Planning and GIS Documantation are still in clarification
The green fields marked with a question mark still need to be discussed with the NAS department to determine whether the tasks should be created or not.
Splicing, blow in fiber, third-party cabling plans, and permit requests are also still being clarified. Initial process meetings with NAS colleagues have already taken place on the topics of third-party cabling plans and permit requests. However, this still needs to be explored in greater depth. There will be an initial process meeting with NAS on the topic of splicing and blow-in fiber. The aim here is to see whether it is possible to build on the processes and building blocks that exist in PPM/FSM for the rollout. There has also already been an initial process meeting on the topic of GIS planning. However, there are still some open points here that need to be explored in more depth. One additional task type is under discusion with NAS. (Surface finaly restroe if it was temporarily closed in task Gardendrilling)
102
101
108
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Es bezieht sich nur auf die Längstrasse
Note on E6: Kamm, Jost: Patchinginfomation über Carrier.
Note on E7: Kamm, Jost: Patching über Carrier
Note on E8: Kamm, Jost: Patching über Carrier
Note on E9: Kamm, Jost: Patching über Carrier
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on E10: Kamm, Jost: Patching über Carrier
Note on I12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den UVS benötigen wir, da der GU sich absichern muss gegen über dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the UVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on V12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde ______________ GFTA only applies to SDU if no single-room solution was discussed in UV_S. 2nd option, if applicable GF-TA is always created during SDU -> if “Single Room Solution YES” is specified in the SDU via UV_S Questionnaires, GFTA WO and WOT are automatically set to Closed Incomplete/Cancelled by the system. GF-TA is created during SDU afterwards and only if “Single Room Solution No” was selected in the UV_S questionnaire. If Single Room Solution Yes is selected, no GF TA is created. Unit deviation from HV_S Questionnaire must be taken into account.
Note on V13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on V14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde
Note on V15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den UVS benötigen wir, da der GU sich absichern muss gegen über dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the UVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on H24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on H28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: According to Legacy, an HV_S is also created if only one PHA NE4 is posted for an address.
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: According to Legacy, an HV_S is also created if only one PHA NE4 is posted for an address.
Note on H30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: According to Legacy, an HV_S is also created if only one PHA NE4 is posted for an address.
Note on E31: Kamm, Jost: Patching über Carrier
Note on E32: Kamm, Jost: Patching über Carrier
Note on H32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on E33: Kamm, Jost: Patching über Carrier
Note on V34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde
Note on H35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on V35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde
Note on V36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GFTA kommt nur bei SDU wenn in UV_S keine Ein Raum Lösung besprochen wurde
Note on H38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on H41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on H44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on J44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.
Note on H45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Den HVS benötigen wir, da der GU sich absichern muss gegenüber dem Kunden. Hier wird die Lage der zu Installierenden Hardware beidseitig vereinbart. ---------------------- We need the HVS (Construction Site Protection System) because the general contractor (GC) needs to protect themselves against the customer. The location of the hardware to be installed is agreed upon by both parties here.

## Set
SDU-GFTAL-HTP
SDU-GFTAL-NE4
MDU-GFTAL-NE4
MDU-PHA Standard-NA
MDU-PHA Full Expansion-NE4
SDU-GFTAL-NE3 (HTP)

## Tasks
Task progress
Task-Typ | Level | info | Template | Attribut | Questionairs | Gates | Milestone | 100 | 101 | 102 | 103 | 105 | 107 | 108 | 109
HV-S | Building |  | X |  | X | Housvisit | 1 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
UV-S | Unit |  | X |  | X | Housvisit | 1 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
HV-NE4 | Building |  | X |  |  | Housvisit | 1 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
UV-NE4 | Unit |  | X |  |  | Housvisit | 1 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
GIS Planung | Unit & Building | overlap | X |  | X | Planning | 2 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
Fremdleitungsplan | Building |  | X |  | X | Planning | 2 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
Genehmigungen | Building |  | X |  | X | Permit | 3 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
Tiefbau | Building |  | X |  | X | Civilwork | 4 | closed or not decomposed | closed or not decomposed | closed or not decomposed | closed or not decomposed | OPEN | closed or not decomposed | closed or not decomposed | closed or not decomposed
Spleißen | Building |  | X |  | X | Mounting NE3 | 5 | closed or not decomposed | closed or not decomposed | closed or not decomposed | closed or not decomposed | OPEN | OPEN | OPEN | OPEN
Einblasen | Building |  | X |  | X | Mounting NE3 | 5 | closed or not decomposed | closed or not decomposed | COMPLETED | closed or not decomposed | OPEN | OPEN | OPEN | OPEN
Gartenbohrung | Building |  | X |  | X | Civilwork | 4 | closed or not decomposed | closed or not decomposed | OPEN | COMPLETED | OPEN | COMPLETED | OPEN | COMPLETED
Hauseinführung | Building |  | X |  | X | ???? |  | closed or not decomposed | closed or not decomposed | OPEN | OPEN | OPEN | COMPLETED | OPEN | OPEN
HÜP | Building |  | X |  | X | Mounting NE3 | 5 | closed or not decomposed | COMPLETED | OPEN | OPEN | OPEN | OPEN | OPEN | OPEN
Leitungsweg NE4 | Building |  | X |  |  | Mounting Inhouse | 6 | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
GFTA | Unit |  | X |  | X | Mounting Inhouse | 6 | closed or not decomposed | open if decomposed | open if decomposed | open if decomposed | open if decomposed | open if decomposed | open if decomposed | open if decomposed
ONT | Unit |  | X |  | X | Mounting Inhouse | 6 | COMPLETED | OPEN | OPEN | OPEN | OPEN | OPEN | OPEN | OPEN
Patch | Unit |  | X |  | X | Mounting NE3 | 5 | COMPLETED | OPEN | OPEN | OPEN | OPEN | OPEN | OPEN | OPEN
GIS Dokumentaion** | Unit & Building | overlap | X |  |  | Documentation |  | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered | unconsidered
Zusatztasks
Zusätzliches Kopfloch | Building
HAS-Störung | Building
Oberflächenwiederherstellung | Building
Genehmigung 127 | Building |  | X
Nachträgliche Wohnungserschließung | Unit
HÜP-Erweiterung | Building
Note on E3: Kamm, Jost: Nur Korpus kein Inhalt
Note on F3: Kamm, Jost: Welche Infos benötigt der GU vor ort. Was zeigt das System an?
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Es bezieht sich nur auf die Längstrasse
Note on A27: Kamm, Jost: Wiederherstellunf der Oberfläche nach vorherigem Provisorium in Tiefbau oder Gartenbohrung.

## Legende
Legende
Tasks werden nicht benötigt
Tasks müssen je nach Lieferstatus erstellt werden
?? | Tasks, die hinterfragt werden müssen
UUID | UniqUe-IDentification | unique id (UUID) = Address point ¦ based on input of House Number + House Number Extn+ Street Name + City + Post Code
Task wird nicht gebraucht

## Overview (hidden)
ORDER | Status code | Account | … | City | Adress | HV-S | UV-S | HV-NE4 | UV-NE4 | GIS Planung | Fremdleitungsplan | Genehmigungen | Tiefbau | Spleißen | Einblasen | Gartenbohrung | Hauseinführung | HÜP | Leitungsweg NE4 | GFTA | ONT | Patch | GIS Dokumentaion**
ORD0012867 | 100 | Test1 Customer |  | Borken | Willbecke 12
ORD0012866 | 101 | Test2 Customer |  | Borken | Willbecke 13
ORD0012865 | 102 | Test3 Customer |  | Borken | Willbecke 14
ORD0012850 | 103 | Test4 Customer |  | Borken | Willbecke 15
ORD0012848 | 108 | Test5 Customer |  | Borken | Willbecke 16
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Es bezieht sich nur auf die Längstrasse

## Overview2
|  |  | 1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  |  | 25 | 26 | 27 |  |  | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 |  | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
|  |  | 49 | 50 | 51 |  |  | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 |  | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72
|  |  | 73 | 74 | 75 |  |  | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 |  | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96
ORDER | Status code | Account | … | City | Adress | Unit | Construction status | HV | UV | HV4 | UV4 | GP | LLD | PM | CV | SP | BF | GD | WB | HÜP | CW4 | GFTA | PCH | ONT | GDOC
ORD0012867 | 100 | Test1 Customer |  | Borken | Willbecke 12 | 2 | [16 empty] | ● | ●
ORD0012866 | 101 | Test2 Customer |  | Borken | Willbecke 13 | 2 | Open | [14 empty] | ○ | ○ | ○ | ○ | bar: 77
ORD0012865 | 102 | Test3 Customer |  | Borken | Willbecke 14 | 1 | [15 empty] | ● | ○ | ● | ○ | bar: 76 to 77; 80 to 82
ORD0012850 | 103 | Test4 Customer |  | Borken | Willbecke 15 | 1 | [15 empty] | ○ | ○ | ○ | ○ | bar: 76 to 77
ORD0012848 | 108 | Test5 Customer |  | Borken | Willbecke 16 | 1 | [13 empty] | ○ |  | ○ | ○ | ○ | ○ | bar: 76 to 77; 80 to 82; 84 to 87
[5 empty] | Option 1 |  | Status | 76: Option 2
not existent
[5 empty] | 2026-04-16 |  | open | bar: 76
[5 empty] | 2026-04-16 |  | scheduled | bar: 76
[5 empty] | 2026-04-16 |  | complet | bar: 76
[5 empty] | 2026-04-16 |  | in progress | bar: 76
[5 empty] | 2026-04-01 |  | Error/Fallout | bar: 76