## Page 1
Number | Consolidated Order Status | Number | Work-Order Number | WorkorderTaskNumber | Number | State | Template | Short description | Assignment group | External id | Account | Contact | Sub Project | Sub Project Name | Actual work start | Actual work end | Task Held Reason | Window start | Window end | Planned End Date
ORD0001472 | Draft | ORDL0001502 | WO0040209 | WOT0047317 | OMTASK000002720 | Work In Progress | Install GFTA | Install GFTA | Field Service_Comtec |  | DG | Ram A |  |  | 2026-05-12 16:51 |  |  | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040210 | WOT0047318 | OMTASK000002720 | Assigned | GIS Documentation -NAS | GIS Documentation -NAS | Assignment Demo Group |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040201 | WOT0047307 | OMTASK000002720 | Pending Dispatch | Standard House Visit | Standard House Visit |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040204 | WOT0047310 | OMTASK000002720 | Pending Dispatch | VRAO Permit | VRAO Permit | Assignment Demo Group |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040202 | WOT0047308 | OMTASK000002720 | Pending Dispatch | Standard Unit Visit | Standard Unit Visit |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040203 | WOT0047309 | OMTASK000002720 | Draft | GIS Planning - NAS | GIS Planning - NAS |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040206 | WOT0047313 | OMTASK000002720 | Pending Dispatch | Wall breakthrough | Wall breakthrough |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040206 | WOT0047312 | OMTASK000002720 | Pending Dispatch | Garden Drilling | Garden Drilling |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040205 | WOT0047311 | OMTASK000002720 | Draft | Aufbruchgenehmigung-NAS | Aufbruchgenehmigung-NAS |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040208 | WOT0047315 | OMTASK000002720 | Pending Dispatch | Install HUP | Install HUP |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040207 | WOT0047316 | OMTASK000002720 | Pending Dispatch | Wall breakthrough | Wall breakthrough |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25
| Draft | ORDL0001502 | WO0040207 | WOT0047314 | OMTASK000002720 | Pending Dispatch | Garden Drilling | Garden Drilling |  |  | DG | Ram A | [5 empty] | 2026-03-03 22:25